School Improvement Plan: Part E – Implementation and Monitoring Progress

Timothy LaGasse

School of Education, Liberty University

Author Note

Timothy LaGasse, I have no known conflict of interest to disclose.

Correspondence concerning this article should be addressed to Timothy LaGasse.

Email: tjlagasse@liberty.edu

Improvement Plan: Part E - Implementation and Monitoring Progress Template

| Goal #1: | Increase the percentage of 8th grade students scoring a three or higher on science open-ended responses from 30% to 45% by the end of the 2026 PSSA cycle through targeted writing interventions and CER instructional strategies. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions, Strategies, and Interventions | Timeline | Estimated Costs, Funding Sources, and Resources | Person(s) Responsible Positions will suffice. Names are unnecessary. | Means of Evaluation |  |
|  |  |  |  | Procedures for Monitoring | Evidence of Impact on Student Learning What will serve as this evidence? |
| - Develop and implement targeted writing lessons focusing on CER (Claim, Evidence, Reasoning) strategies. - Integrate open-ended question practice into weekly science instruction. - Collaborate with grade-level teams and instructional coaches to align writing expectations. - Use anchor papers and student exemplars to guide instruction and self-assessment. | Fall 2025 through Spring 2026 | Approx. $2,500 for instructional materials and online tools. Funded through Title I and curriculum department budgets. | Middle School Science Teachers, Department Chair, Instructional Coaches | PSSA science open-ended rubric scores, teacher-created benchmark writing tasks | Growth in rubric scores, increased student confidence in writing, improved PSSA performance data. |

| Goal #2: | By December 2025, provide a minimum of three professional development sessions focused on scientific writing and CER strategies for middle school science teachers. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions, Strategies, and Interventions | Timeline | Estimated Costs, Funding Sources, and Resources | Person(s) Responsible Positions will suffice. Names are unnecessary. | Means of Evaluation |  |
|  |  |  |  | Procedures for Monitoring | Evidence of Impact on Student Learning What will serve as this evidence? |
| Plan and deliver 3 PD sessions with focus on CER instruction and assessment. - Use teacher feedback to adjust session content and delivery. - Incorporate model lessons, peer collaboration, and CER anchor materials. | Fall 2025 – December 2025 | Estimated $3,000 for guest facilitators, and PD materials. Funded by PD budget and grant funds. | Department Chair, PD Coordinator, Academic Directors | Ongoing feedback collection and reflective evaluations after each session. | Increased teacher comfort with CER, more consistent CER instruction in lesson plans, improved student writing quality. |

| Goal #3: | By February 2026, implement a digital CER practice tool or scaffolded writing module across all middle school science classes. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions, Strategies, and Interventions | Timeline | Estimated Costs, Funding Sources, and Resources | Person(s) Responsible Positions will suffice. Names are unnecessary. | Means of Evaluation |  |
|  |  |  |  | Procedures for Monitoring | Evidence of Impact on Student Learning What will serve as this evidence? |
| - Identify and vet available digital platforms for CER writing practice. - Pilot digital tools with selected classes before full rollout. - Train staff on usage and implementation during PD sessions. - Monitor student progress and adapt modules based on feedback. | Spring 2025 – February 2026 | $5,000 for platform licensing and integration. Funded through technology and curriculum budgets. | Department Char, Tech coordinator, science teachers | Usage reports, student surveys, teacher feedback logs. | Improved consistency and frequency of CER practice, digital progress tracking aligned to science standards. |

| Goal #4: | By May 2026, family engagement in science writing support will increase by 25% through the introduction of monthly virtual science-writing workshops and parent guides. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Actions, Strategies, and Interventions | Timeline | Estimated Costs, Funding Sources, and Resources | Person(s) Responsible Positions will suffice. Names are unnecessary. | Means of Evaluation |  |
|  |  |  |  | Procedures for Monitoring | Evidence of Impact on Student Learning What will serve as this evidence? |
| - Host monthly virtual workshops for families on how to support CER writing at home. - Develop and distribute science-writing parent guides with tips and examples. - Partner with family engagement liaisons to promote and support attendance. - Survey families before and after sessions to guide improvements. | Fall 2025 – May 2026 | $1,200 for platform use, materials, and translation services. Funded by family engagement grants and school funds. | Family Engagement Coordinator, Science Teachers, Department Chair | Monthly review of attendance and feedback, resources based on family needs. | Higher family participation, stronger student writing habits, positive feedback from families on support tools. |

References

BoardOnTrack. (2025, April 15). Middle school leadership improvement plan report

https://app2.boardontrack.com/org/X8qMBm/attachment/publicDownload/359663?	s=X8qMBm

Reach Cyber Charter School https://www.liberty.edu/casas/academic-success-center/wp-	content/uploads/sites/28/2020/04/Sample-Paper-APA-7th-professional-version-	06172020.pdf